## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Project (Fraud Detection System Overview) | MUST HAVE | No Dependency | Sriramachandran | 3 - Completed
S1 | S1 | US-002 | System Architecture & Workflow Design | MUST HAVE | Lucid Chart | Shivathmika | 3 - Completed
S2 | S2 | US-003 | Agile Documentation (Backlog, User Stories, Testing Plan) | MUST HAVE | No Dependency | Shivathmika | 3 - Completed
S2 | S2 | US-004 | Fraud Use Case Research & Dataset Analysis | SHOULD HAVE | Kaggle Dataset | Sriramachandran | 3 - Completed
S3 | S3 | US-005 | Machine Learning Model Development (Fraud Detection) | MUST HAVE | Python, Sklearn | Sriramachandran | 3 - Completed
S4 | S4 | US-006 | Database Design & SQL Integration | MUST HAVE | MySQL | Shivathmika | 3 - Completed
S5 | S5 | US-007 | Backend API Development (/mlFraudCheck, Alerts) | MUST HAVE | Flask, REST APIs | Sriramachandran | 3 - Completed
S6 | S6 | US-008 | Email Alert Integration (SMTP Fraud Alerts) | SHOULD HAVE | Gmail SMTP | Shivathmika | 3 - Completed
S7 | S7 | US-009 | Frontend Dashboard Development (React UI) | SHOULD HAVE | React, Axios | Shivathmika | 3 - Completed
S8 | S8 | US-010 | System Testing, Deployment & Optimization | MUST HAVE | Render | Sriramachandran | 3 - Comlpeted
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 71 | 19 | 16 | 12 | 8 | 7 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project Introduction & Requirement Analysis | 2026-02-07 | 2026-02-08 | Shivathmika | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | System Architecture & Workflow Design | 2026-02-09 | 2026-02-11 | Sriramchandran | Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Agile Documentation (Backlog, Stories) | 2026-02-12 | 2026-02-13 | Shivathmika | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Dataset Collection & Research | 2026-02-14 | 2026-02-17 | Shivathmika | Research | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | ML Model Development & Training | 2026-02-18 | 2026-02-24 | Sriramchandran | Coding | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Database Design & SQL Integration | 2026-02-25 | 2026-02-28 | Sriramchandran | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Backend API Development (/mlFraudCheck) | 2026-03-01 | 2026-03-05 | Shivathmika | Build | 3- Completed | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Email Alert Integration (SMTP Setup) | 2026-03-06 | 2026-03-10 | Sriramchandran | Coding | 2- In Progress | 9 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Frontend Dashboard Development (React UI) | 2026-03-11 | 2026-03-17 | Shivathmika | Integration | 2- In Progress | 10 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | System Testing & Deployment | 2026-03-18 | 2026-03-23 | Sriramchandran | Testing | 2- In Progress | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding Agile documentation and template | Reviewed Agile concepts and clarified with mentor
Sprint 2 | Day 6 | Difficulty selecting suitable dataset for fraud detection | Explored Kaggle datasets and finalized dataset
Sprint 2 | Day 9 | Confusion in prioritizing system features (ML, UI, Alerts) | Created priority matrix to rank features
Sprint 3 | Day 12 | Issues in ML model training and low accuracy | Tuned model parameters and tested multiple algorithms
Sprint 3 | Day 14 | Difficulty handling edge cases in fraud prediction | Improved preprocessing and feature selection
Sprint 4 | Day 16 | SQL queries slow during transaction storage | Optimized queries and improved indexing
Sprint 4 | Day 18 | Issues connecting backend (Flask) with database | Fixed DB configuration and connection errors
Sprint 4 | Day 20 | API integration issues between frontend and backend | Resolved API endpoints and payload mismatches
Sprint 5 | Day 23 | CORS errors while connecting React with Flask | Enabled CORS and fixed headers
Sprint 5 | Day 26 | Email alerts not sending (SMTP configuration error) | Configured Gmail App Password and fixed SMTP setup
Sprint 6 | Day 28 | Email format not clear and user-friendly | Redesigned email template with proper details
Sprint 6 | Day 30 | Real-time alerts not updating in dashboard | Implemented WebSocket for live updates
Sprint 6 | Day 32 | Delay in UI rendering of fraud alerts | Optimized frontend state updates
Sprint 7 | Day 34 | Issues in testing full system integration | Performed integration testing and fixed bugs
Sprint 7 | Day 36 | Minor UI bugs and inconsistencies | Debugged and refined UI components
Sprint 8 | Day 40 | Deployment issues on server environment | Fixed environment variables and deployment configs
Sprint 8 | Day 42 | Performance optimization challenges | Improved API response time and reduced latency

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-07 | 2026-02-14 | Sriramchandran, Shivathmika | Understanding requirements and planning system architecture | Assuming requirements without discussion | Participating in team discussions | Finalized project scope and workflow with mentor
2 | Sprint 2 | 2026-02-15 | 2026-02-24 | Sriramchandran | Developing ML model and preparing dataset | Using single model approach | Testing multiple models | Improved model accuracy using tuning and feature selection
3 | Sprint 3 | 2026-02-25 | 2026-03-10 | Sriramchandran, Shivathmika | Backend API development and frontend integration | Ignoring integration issues | Collaborative debugging | Successfully integrated Flask backend with React frontend
4 | Sprint 4 | 2026-03-11 | 2026-03-23 | Shivathmika | Testing, UI improvement, and deployment | Ignoring minor UI bugs | Continuous testing and improvements | Completed testing and prepared system for deployment